## PMs_per_ partner (3)
Costs
| PROJECT PLAN DAWN - Near | week | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | Hours | Material Costs | Personel Costs | Amount
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  |  |  | USD
WP1 | CREATING KNOWLEDGE | bar: 1 to 24
T1.1 | Creation of promotional materials for Panel Discussion & communication campaign | [24 empty] | 24 |  | Promo material design, social media posts | 600 | bar: 1 to 6
T1.1 | Creating research design framework for the panel discusion | [24 empty] | 32 |  | Content production | 800 | bar: 1 to 6
T1.2 | Organising panel discussion | [24 empty] | 32 | rental, drinks, food, 9500 | Payments to guests participants, filming, 6500 | 16000 | bar: 1 to 8
T1.5 | Data analysis : transcribing data from the dicsussion, qualitative anaylsis | [24 empty] | 32 |  | Data analysis | 800 | bar: 6 to 12
T1.6 | Writing scientific or professional article | [24 empty] | 40 |  | Content production | 1800 | bar: 6 to 12
T1.7 | Scientific or professional article publishing review, evaluation of results | [24 empty] | 16 | publishing fee, 2500 | Content production, 500 | 3000 | bar: 11 to 17
T1.8 | Development of solutions, guidelines and recommendations in Future Research & Innovation Agenda | [24 empty] | 32 |  | Content production | 600 | bar: 11 to 17
WP2 | TRANSFERRING KNOWLEDGE | bar: 1 to 24
T2.1 | Writing first blog on Medium.com and DAWN web page. | [24 empty] | 12 |  | Content production | 400 | bar: 13 to 18
T2.2 | Creation of promotional materials for webinar & communication campaign | [24 empty] | 8 |  | Promo material design, social media posts | 400 | bar: 13 to 18
T2.3 | Development and launching of the webinar. | [24 empty] | 32 |  | Content production + video | 1600 | bar: 16 to 19
T2.4 | Writing second blog on Medium.com and DAWN web page. | [24 empty] | 12 |  | Content production | 400 | bar: 16 to 19
T2.5 | Creation of promotional materials for Workshop & communication campaign | [24 empty] | 8 |  | Promo material design, social media posts | 400 | bar: 17 to 21
T2.6 | Writing third blog on Medium.com and DAWN web page. | [24 empty] | 12 |  | Content production | 600 | bar: 17 to 21
T2.7 | Creation of promotional video and other promo materials for Final Event & communication campaign | [24 empty] | 92 |  | Promo material design, social media posts | 600 | bar: 17 to 21
T2.8 | Development and conducting workshop for practical guidelines of digital representation of a green area on the blockchain in a shape of NFT. | [24 empty] | 40 | rental, drinks, food, 2000 | Payments to moderator and lecturer, filming, 5000 | 7000 | bar: 19 to 23
T2.9 | Organization of 1 final event/ party in Vienna in high end location | [24 empty] | 32 | rental, drinks, food, 15000 | Payments to guest speakers, filming, 12000 | 32000 | bar: 22 to 24
T2.10 | Creation and maintenance of DAWN Knowledge Repository Web page with Online Community section | [24 empty] | 100 | domain, 250 | Design, maintenance, and content production | 5000
T2.11 | Project coordination and administration and financial management | [24 empty] | 100 |  | Management | 2500 | bar: 1 to 24
T2.12 | Data management, security and monitoring | [24 empty] | 24 |  | Management | 300
T2.13 | Research ethics management and monitoring | [24 empty] | 16 |  | Management | 300
[26 empty] | 696 |  |  | 75100

## Deliverables
D# | Deliverable name | WP# | Nature | Dissemination level | Delivery date (month) | responsible partner |  | D# | Deliverable name | WP# | Nature | Dissemination level | Delivery date (month)
1.1 | Kick-off meeting report | 1 | R | CO | 2 |  | 1 | 1.1 | Kick-off meeting report | 1 | R | CO | 2
1.2 | Data management plan | 1 | R | CO | 6 |  | 2 | 7.1 | Project website, social media channels and communication activities | 7 | O | PU | 3
1.3 | Ethical framework | 1 | R | CO | 6 |  | 3 | 2.1 | Stakeholder overview, involvement roadmap & engagement strategy | 2 | R | CO | 5
1.4 | Final project documentation | 1 | R | CO | 36 |  | 4 | 7.2 | Dissemination, Exploitation and Communication plan | 7 | R | RE | 5
2.1 | Stakeholder overview, involvement roadmap & engagement strategy | 2 | R | CO | 5 |  | 5 | 1.2 | Data management plan | 1 | R | CO | 6
2.2 | Literature analysis on digital technologies for education | 2 | R | PU | 6 |  | 6 | 1.3 | Ethical framework | 1 | R | CO | 6
2.3 | Interview summary report | 2 | R | PU | 7 |  | 7 | 2.2 | Literature analysis on digital technologies for education | 2 | R | PU | 6
2.4 | Survey summary report | 2 | R | PU | 10 |  | 8 | 2.3 | Interview summary report | 2 | R | PU | 7
2.5 | Baseline report | 2 | R | PU | 12 |  | 9 | 3.1 | Challenge concept | 3 | R | CO | 8
2.6 | Update on Baseline report | 2 | R | PU | 28 |  | 10 | 3.2 | ETHUCATION Challenge Toolkits | 3 | O | PU | 9
3.1 | Challenge concept | 3 | R | CO | 8 |  | 11 | 2.4 | Survey summary report | 2 | R | PU | 10
3.2 | ETHUCATION Challenge Toolkits | 3 | O | PU | 9 |  | 12 | 4.1 | DigiBridge web platform early prototype | 4 | O | PU | 10
3.3 | Report on stakeholder mobilisation | 3 | R | CO | 18 |  | 13 | 4.2 | Open Information Hub | 4 | O | PU | 11
4.1 | DigiBridge web platform early prototype | 4 | O | PU | 10 |  | 14 | 2.5 | Baseline report | 2 | R | PU | 12
4.2 | Open Information Hub | 4 | O | PU | 11 |  | 15 | 4.3 | Submission system progress report | 4 | R | RE | 13
4.3 | Submission system progress report | 4 | R | RE | 13 |  | 16 | 6.1 | Training programmes requirements | 6 | R | PU | 13
4.4 | Training modules progress report | 4 | R | RE | 14 |  | 17 | 4.4 | Training modules progress report | 4 | R | RE | 14
4.5 | Platform content implmementation report | 4 | R | RE | 34 |  | 18 | 5.1 | Awareness raising and promotion summary report | 5 | R | PU | 16
5.1 | Awareness raising and promotion summary report | 5 | R | PU | 16 |  | 19 | 3.3 | Report on stakeholder mobilisation | 3 | R | CO | 18
5.2 | Deployment pilot summary report | 5 | R | PU | 35 |  | 20 | 7.3 | Update on Dissemination, Exploitation and Communication plan | 7 | R | RE | 23
5.3 | Pilot evaluation report | 5 | R | PU | 36 |  | 21 | 2.6 | Update on Baseline report | 2 | R | PU | 28
6.1 | Training programmes requirements | 6 | R | PU | 13 |  | 22 | 6.2 | Workshops summary report | 6 | R | PU | 32
6.3 | Training programmes & training materials | 3 | R | PU | 33 |  | 23 | 6.3 | Training programmes & training materials | 3 | R | PU | 33
6.2 | Workshops summary report | 6 | R | PU | 32 |  | 24 | 4.5 | Platform content implmementation report | 4 | R | RE | 34
6.4 | Strategy for Digital Education in Remote Areas | 6 | R | PU | 36 |  | 25 | 5.2 | Deployment pilot summary report | 5 | R | PU | 35
7.1 | Project website, social media channels and communication activities | 7 | O | PU | 3 |  | 26 | 1.4 | Final project documentation | 1 | R | CO | 36
7.2 | Dissemination, Exploitation and Communication plan | 7 | R | RE | 5 |  | 27 | 5.4 | Pilot evaluation report | 5 | R | PU | 36
7.3 | Update on Dissemination, Exploitation and Communication plan | 7 | R | RE | 23 |  | 28 | 6.4 | Strategy for Digital Education in Remote Areas | 6 | R | PU | 36
7.4 | Policy materials | 7 | O | RE | 36 |  | 29 | 7.4 | Policy materials | 7 | O | RE | 36
7.5 | Dissemination, Exploitaiton and Communication activities report | 7 | R | PU | 36 |  | 30 | 7.5 | Dissemination, Exploitaiton and Communication activities report | 7 | R | PU | 36